**Elijah Perry Park Remediation**

**August, 2023**

The Elijah Perry Park remediation will include removal of approximately 6,900 tons of historic ﬁll material. The anticipated soil disposal facility is Kinsley’s Landfill located at 2025 Delsea Drive in Sewell, NJ 08080. When remediation of historic ﬁll material is complete, the Park construction of improvements work will begin by installing new park features.

The remediation contractor, Ambient, estimates a maximum of 50 trucks per day and work hours will be 7:00 AM – 3:30 PM. No vehicles shall be staged on the right-of-way.

Current Schedule as of Date

|  |  |  |
| --- | --- | --- |
| Task | Start | Finish |
| Mobilization, Site Preparation, SESC Controls | 8/24/2023 |  |
| Equipment Mobilization |  |  |
| Install SESC Controls, Construction Entrance |  |  |
| Install Temporary Construction Fence | 8/29/2023 | 8/31/2023 |
| Site Clearing |  |  |
| Remove Existing Features Including Trees, Playground Equipment, Demolish Concrete | 9/6/2023 | 9/11/2023 |
| Disposal of Historic Fill - |  |  |
| Excavation, Loading, Transportation and Disposal of Historic Fill | 9/11/2023 | 9/22/2023 |
| Site Restoration |  |  |
| Install Demarcation Fence, Import and Place Clean Fill, Grading | 9/22/2023 | 10/4/2023 |
| Demobilization |  |  |
| Cleanup, Equipment Demobilization | 10/04/23 | 10/6/2023 |